## Issue Tracker
| OPEN vs. CLOSED ISSUE TRACKER |  |  |  |  | TYPE | PRIORITY | DATE | LAST (days)
[6 empty] | * | * | 2024-05-30 | 30
Issue Tracker Chart showing Opened vs. Closed issues per day for a given time frame is in cells A2 through J4.
| # | ISSUE | TYPE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
| 1 | Issue #1 | Type 2 | Medium | 2024-02-01 | James | 2024-02-04 | James
| 2 | Issue #2 | Type 2 | Low | 2024-02-01 | Kim | 2024-02-01 | James
| 3 | Issue #3 | Type 3 | Low | 2024-02-04 | Lilly | 2024-02-04 | Lilly
| 4 | Issue #4 | Type 1 | Medium | 2024-02-04 | Lilly | 2024-02-05 | Lilly
| 5 | Issue #5 | Type 1 | Medium | 2024-02-04 | James | 2024-02-04 | Ted
| 6 | Issue #6 | Type 1 | Low | 2024-02-08 | Ted | 2024-02-08 | James
| 7 | Issue #7 | Type 1 | High | 2024-02-08 | Kim | 2024-02-13 | James
| 8 | Issue #8 | Type 2 | Medium | 2024-02-08 | Kim | 2024-02-11 | James
| 9 | Issue #9 | Type 3 | Medium | 2024-02-08 | Kim | 2024-02-11 | Kim
| 10 | Issue #10 | Type 4 | High | 2024-02-12 | Ted | 2024-02-12 | Lilly
| 11 | Issue #11 | Type 2 | Medium | 2024-02-12 | Kim | 2024-02-13 | Lilly
| 12 | Issue #12 | Type 1 | High | 2024-02-15 | Ted | 2024-02-18 | James
| 13 | Issue #13 | Type 2 | High | 2024-02-20 | Kim | 2024-02-20 | Kim
| 14 | Issue #14 | Type 2 | High | 2024-02-23 | Ted | 2024-02-23 | James
| 15 | Issue #15 | Type 2 | Low | 2024-02-26 | James | 2024-02-27 | Lilly
| 16 | Issue #16 | Type 4 | Medium | 2024-02-26 | Lilly | 2024-02-26 | James
| 17 | Issue #17 | Type 2 | Low | 2024-02-26 | Ted | 2024-02-26 | Ted
| 18 | Issue #18 | Type 3 | High | 2024-02-27 | Lilly | 2024-02-27 | Lilly
| 19 | Issue #19 | Type 2 | Low | 2024-02-27 | Ted | 2024-02-27 | Lilly
| 20 | Issue #20 | Type 3 | Low | 2024-03-04 | Lilly | 2024-03-04 | Ted
| 21 | Issue #21 | Type 4 | Low | 2024-03-04 | Lilly | 2024-03-07 | Kim
| 22 | Issue #22 | Type 3 | Low | 2024-03-04 | Ted | 2024-03-09 | Kim
| 23 | Issue #23 | Type 3 | Medium | 2024-03-05 | Kim | 2024-03-05 | James
| 24 | Issue #24 | Type 3 | Medium | 2024-03-05 | Lilly | 2024-03-05 | James
| 25 | Issue #25 | Type 1 | High | 2024-03-06 | Kim | 2024-03-10 | Ted
| 26 | Issue #26 | Type 1 | High | 2024-03-06 | Kim | 2024-03-08 | Kim
| 27 | Issue #27 | Type 1 | High | 2024-03-06 | James | 2024-03-08 | Ted
| 28 | Issue #28 | Type 4 | Low | 2024-03-11 | Ted | 2024-03-12 | James
| 29 | Issue #29 | Type 3 | Low | 2024-03-12 | Kim | 2024-03-13 | Kim
| 30 | Issue #30 | Type 2 | Medium | 2024-03-12 | Lilly | 2024-03-13 | Kim
| 31 | Issue #31 | Type 4 | Medium | 2024-03-17 | Lilly | 2024-03-19 | James
| 32 | Issue #32 | Type 4 | Low | 2024-03-21 | Ted | 2024-03-26 | James
| 33 | Issue #33 | Type 4 | Low | 2024-03-25 | James | 2024-03-26 | Lilly
| 34 | Issue #34 | Type 3 | Low | 2024-03-25 | Kim | 2024-03-30 | Lilly
| 35 | Issue #35 | Type 1 | Low | 2024-03-29 | James | 2024-03-29 | Kim
| 36 | Issue #36 | Type 4 | Medium | 2024-03-31 | Ted | 2024-04-04 | Lilly
| 37 | Issue #37 | Type 4 | Medium | 2024-04-05 | James | 2024-04-06 | Lilly
| 38 | Issue #38 | Type 2 | High | 2024-04-09 | Lilly | 2024-04-14 | James
| 39 | Issue #39 | Type 4 | Low | 2024-04-10 | Lilly | 2024-04-12 | Ted
| 40 | Issue #40 | Type 3 | Low | 2024-04-10 | Ted | 2024-04-13 | Lilly
| 41 | Issue #41 | Type 4 | Low | 2024-04-12 | James | 2024-04-13 | James
| 42 | Issue #42 | Type 1 | Medium | 2024-04-16 | Kim | 2024-04-16 | Ted
| 43 | Issue #43 | Type 2 | Medium | 2024-04-18 | Lilly | 2024-04-18 | Kim
| 44 | Issue #44 | Type 1 | Medium | 2024-04-18 | Ted | 2024-04-22 | Kim
| 45 | Issue #45 | Type 1 | Medium | 2024-04-22 | Lilly | 2024-04-23 | Kim
| 46 | Issue #46 | Type 2 | High | 2024-04-23 | James | 2024-04-24 | Kim
| 47 | Issue #47 | Type 1 | Medium | 2024-04-25 | Ted | 2024-04-25 | Lilly
| 48 | Issue #48 | Type 3 | Medium | 2024-04-30 | Ted | 2024-05-01 | Kim
| 49 | Issue #49 | Type 1 | Medium | 2024-05-05 | Lilly | 2024-05-05 | Ted
| 50 | Issue #50 | Type 2 | Medium | 2024-05-05 | Kim | 2024-05-09 | James
| 51 | Issue #51 | Type 2 | High | 2024-05-08 | James | 2024-05-12 | Kim
| 52 | Issue #52 | Type 3 | Low | 2024-05-11 | James | 2024-05-14 | Ted
| 53 | Issue #53 | Type 4 | Medium | 2024-05-11 | James | 2024-05-11 | Ted
| 54 | Issue #54 | Type 1 | Low | 2024-05-12 | James | 2024-05-12 | Ted
| 55 | Issue #55 | Type 1 | Low | 2024-05-15 | Ted | 2024-05-15 | James
| 56 | Issue #56 | Type 1 | Medium | 2024-05-17 | Lilly | 2024-05-17 | Lilly
| 57 | Issue #57 | Type 1 | High | 2024-05-17 | Lilly | 2024-05-21 | Kim
| 58 | Issue #58 | Type 1 | High | 2024-05-17 | Lilly | 2024-05-19 | Lilly
| 59 | Issue #59 | Type 3 | Medium | 2024-05-21 | Kim | 2024-05-21 | Ted
| 60 | Issue #60 | Type 3 | High | 2024-05-24 | Ted | 2024-05-26 | Kim
| 61 | Issue #61 | Type 2 | Medium | 2024-05-25 | Kim | 2024-05-25 | Lilly
| 62 | Issue #62 | Type 3 | Low | 2024-05-30 | Lilly | 2024-06-03 | James
| 63 | Issue #63 | Type 4 | Low | 2024-06-04 | James | 2024-06-04 | James
| 64 | Issue #64 | Type 4 | Low | 2024-06-07 | Ted | 2024-06-09 | Ted
| 65 | Issue #65 | Type 4 | High | 2024-06-07 | Ted | 2024-06-07 | James
| 66 | Issue #66 | Type 4 | Medium | 2024-06-12 | Kim | 2024-06-12 | Kim
| 67 | Issue #67 | Type 1 | Medium | 2024-06-17 | Ted | 2024-06-17 | James
| 68 | Issue #68 | Type 4 | Low | 2024-06-18 | Lilly | 2024-06-18 | James
| 69 | Issue #69 | Type 3 | Medium | 2024-06-18 | James | 2024-06-18 | Lilly
| 70 | Issue #70 | Type 4 | High | 2024-06-18 | Lilly | 2024-06-18 | Kim
| 71 | Issue #71 | Type 3 | High | 2024-06-19 | James | 2024-06-19 | Lilly
| 72 | Issue #72 | Type 2 | High | 2024-06-23 | Ted | 2024-06-23 | James
| 73 | Issue #73 | Type 4 | Low | 2024-06-28 | James | 2024-06-30 | Kim
| 74 | Issue #74 | Type 1 | Low | 2024-06-28 | Kim | 2024-06-28 | Kim
| 75 | Issue #75 | Type 4 | High | 2024-07-03 | James | 2024-07-03 | Kim
| 76 | Issue #76 | Type 3 | High | 2024-07-04 | Kim | 2024-07-08 | Ted
| 77 | Issue #77 | Type 2 | High | 2024-07-04 | Ted | 2024-07-04 | Kim
| 78 | Issue #78 | Type 2 | High | 2024-07-05 | Ted | 2024-07-10 | Lilly
| 79 | Issue #79 | Type 4 | Medium | 2024-07-10 | James | 2024-07-15 | Lilly
| 80 | Issue #80 | Type 1 | High | 2024-07-10 | Ted | 2024-07-12 | James
| 81 | Issue #81 | Type 4 | High | 2024-07-11 | Lilly | 2024-07-13 | Ted
| 82 | Issue #82 | Type 1 | High | 2024-07-15 | Lilly | 2024-07-18 | Kim
| 83 | Issue #83 | Type 4 | High | 2024-07-17 | Kim | 2024-07-20 | Ted
| 84 | Issue #84 | Type 2 | Low | 2024-07-20 | James | 2024-07-20 | Lilly
| 85 | Issue #85 | Type 1 | Medium | 2024-07-23 | James | 2024-07-23 | Ted
| 86 | Issue #86 | Type 3 | Medium | 2024-07-28 | Kim | 2024-07-28 | Kim
| 87 | Issue #87 | Type 2 | Medium | 2024-07-28 | Lilly | 2024-08-02 | Kim
| 88 | Issue #88 | Type 2 | Medium | 2024-07-31 | Ted | 2024-07-31 | James
| 89 | Issue #89 | Type 3 | High | 2024-08-02 | Kim | 2024-08-06 | Lilly
| 90 | Issue #90 | Type 4 | Medium | 2024-08-06 | Kim | 2024-08-06 | James
| 91 | Issue #91 | Type 2 | High | 2024-08-08 | Kim | 2024-08-10 | Lilly

## calculations (hidden)
*** This sheet should remain hidden ***
|  |  | Min | 2023-01-01
Max
|  |  | Days | 30
|  |  | Date | 2024-05-30 | 0
|  |  | Type | *
|  |  | Priority | *
[5 empty] | #VALUE! | #VALUE!
[5 empty] | 4 | 3 | Sorted | Sorted
|  | Date | Opened | Closed | Types | Priorities | Types | Priorities
[5 empty] | * | *
| 1 | 2024-05-01 | 0 | 1 | Type 2 | Medium | * | *
| 2 | 2024-05-02 | 0 | 1 | Type 3 | Low | Type 1 | High
| 3 | 2024-05-03 | 0 | 1 | Type 1 | High | Type 2 | Low
| 4 | 2024-05-04 | 0 | 1 | Type 4 | #N/A | Type 3 | Medium
| 5 | 2024-05-05 | 2 | 2 | #N/A | #N/A | Type 4 | #NUM!
| 6 | 2024-05-06 | 2 | 2 | #N/A | #N/A | #NUM! | #NUM!
| 7 | 2024-05-07 | 2 | 2 | #N/A | #N/A | #NUM! | #NUM!
| 8 | 2024-05-08 | 3 | 2 | #N/A | #N/A | #NUM! | #NUM!
| 9 | 2024-05-09 | 3 | 3 | #N/A | #N/A | #NUM! | #NUM!
| 10 | 2024-05-10 | 3 | 3 | #N/A | #N/A | #NUM! | #NUM!
| 11 | 2024-05-11 | 5 | 4 | #N/A | #N/A | #NUM! | #NUM!
| 12 | 2024-05-12 | 6 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 13 | 2024-05-13 | 6 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 14 | 2024-05-14 | 6 | 7 | #N/A | #N/A | #NUM! | #NUM!
| 15 | 2024-05-15 | 7 | 8 | #N/A | #N/A | #NUM! | #NUM!
| 16 | 2024-05-16 | 7 | 8 | #N/A | #N/A | #NUM! | #NUM!
| 17 | 2024-05-17 | 10 | 9 | #N/A | #N/A | #NUM! | #NUM!
| 18 | 2024-05-18 | 10 | 9 | #N/A | #N/A | #NUM! | #NUM!
| 19 | 2024-05-19 | 10 | 10 | #N/A | #N/A | #NUM! | #NUM!
| 20 | 2024-05-20 | 10 | 10 | #N/A | #N/A | #NUM! | #NUM!
| 21 | 2024-05-21 | 11 | 12 | #N/A | #N/A | #NUM! | #NUM!
| 22 | 2024-05-22 | 11 | 12 | #N/A | #N/A | #NUM! | #NUM!
| 23 | 2024-05-23 | 11 | 12 | #N/A | #N/A | #NUM! | #NUM!
| 24 | 2024-05-24 | 12 | 12 | #N/A | #N/A | #NUM! | #NUM!
| 25 | 2024-05-25 | 13 | 13 | #N/A | #N/A | #NUM! | #NUM!
| 26 | 2024-05-26 | 13 | 14 | #N/A | #N/A | #NUM! | #NUM!
| 27 | 2024-05-27 | 13 | 14 | #N/A | #N/A | #NUM! | #NUM!
| 28 | 2024-05-28 | 13 | 14 | #N/A | #N/A | #NUM! | #NUM!
| 29 | 2024-05-29 | 13 | 14 | #N/A | #N/A | #NUM! | #NUM!
| 30 | 2024-05-30 | 14 | 14 | #N/A | #N/A | #NUM! | #NUM!
| 31 | 2024-05-31 | 14 | 14
| 32 | 2024-06-01 | 14 | 14
| 33 | 2024-06-02 | 14 | 14
| 34 | 2024-06-03 | 14 | 15
| 35 | 2024-06-04 | 15 | 16
| 36 | 2024-06-05 | 15 | 16
| 37 | 2024-06-06 | 15 | 16
| 38 | 2024-06-07 | 17 | 17
| 39 | 2024-06-08 | 17 | 17
| 40 | 2024-06-09 | 17 | 18
| 41 | 2024-06-10 | 17 | 18
| 42 | 2024-06-11 | 17 | 18
| 43 | 2024-06-12 | 18 | 19
| 44 | 2024-06-13 | 18 | 19
| 45 | 2024-06-14 | 18 | 19
| 46 | 2024-06-15 | 18 | 19
| 47 | 2024-06-16 | 18 | 19
| 48 | 2024-06-17 | 19 | 20
| 49 | 2024-06-18 | 22 | 23
| 50 | 2024-06-19 | 23 | 24
| 51 | 2024-06-20 | 23 | 24
| 52 | 2024-06-21 | 23 | 24
| 53 | 2024-06-22 | 23 | 24
| 54 | 2024-06-23 | 24 | 25
| 55 | 2024-06-24 | 24 | 25
| 56 | 2024-06-25 | 24 | 25
| 57 | 2024-06-26 | 24 | 25
| 58 | 2024-06-27 | 24 | 25
| 59 | 2024-06-28 | 26 | 26
| 60 | 2024-06-29 | 26 | 26
| 61 | 2024-06-30 | 26 | 27
| 62 | 2024-07-01 | 26 | 27
| 63 | 2024-07-02 | 26 | 27
| 64 | 2024-07-03 | 27 | 28
| 65 | 2024-07-04 | 29 | 29