## Free Wedding Timeline
Free Wedding Timeline
DONE?
| 9 - 12 | ☐ | Arrange a gathering for you and your parents.
|  | ☐ | Determine budget and how expenses will be shared.
| MONTHS TO GO | ☐ | Discuss the size, style, location, and scope of the wedding you want.
|  | ☐ | Choose a target wedding date and time. (The actual date will depend on venue availability.)
|  | ☐ | Create a binder to store and organize ideas, worksheets, receipts, brochures, etc.
|  | ☐ | Visit and reserve wedding and reception sites.
|  | ☐ | Meet with your officiant.
|  | ☐ | Start compiling your guest list to estimate head count. Consider budget when thinking about “must-invites” versus “nice-to-invites.”
|  | ☐ | Begin shopping for the wedding gown.
| 6 - 9 | ☐ | Choose the members of your wedding party.
|  | ☐ | Enroll in wedding/shower gift registries.
| MONTHS TO GO | ☐ | Hire a photographer and a videographer.
|  | ☐ | Book an engagement photo session, especially if you plan to include a professional engagement picture with Save-the-Date cards.
|  | ☐ | Hire a caterer.
|  | ☐ | Hire a florist.
|  | ☐ | Make arrangements for music to be played at the ceremony and reception. (Tasks might include booking a band or solo musician, hiring a DJ, choosing significant musical selections, and so on.).
|  | ☐ | Reserve a block of hotel rooms for out-of-town guests. (Ask about group rates.)
|  | ☐ | Send out Save-the-Date cards. (Include lodging info and maps, as possible.)
|  | ☐ | Shop for wedding rings.
|  | ☐ | Select and order wedding gown, leaving ample time for delivery and alterations.
|  | ☐ | Shop for bridesmaids dresses.
|  | ☐ | Schedule wedding cake design appointments and tastings.
|  | ☐ | Start planning your honeymoon.
| 4 - 6 | ☐ | Finalize the guest list.
|  | ☐ | Order invitations and other wedding stationery.
| MONTHS TO GO | ☐ | Plan wedding-day beauty preparations; ask your stylist how far in advance they book wedding parties, and whether they are willing to work on the wedding site.
|  | ☐ | Finalize all honeymoon plans. If traveling outside the country, arrange for visas, passports and inoculations.
|  | ☐ | Hire your wedding day transportation (carriage, limousine service, etc.).
|  | ☐ | Plan the rehearsal dinner.
| 2 - 4 | ☐ | Obtain a marriage license. Bring all necessary documents.
|  | ☐ | Order tuxedoes for the groom and groomsmen.
| MONTHS TO GO | ☐ | Meet with the caterer to go over menus, wine selections, etc.
|  | ☐ | Order the wedding cake.
|  | ☐ | Order your wedding rings.
|  | ☐ | Confirm wedding ceremony and reception music.
|  | ☐ | Book a hotel room for the wedding night.
|  | ☐ | If you plan on writing your own vows, start writing them now.
| 4 - 8 | ☐ | Mail the wedding invitations 8 weeks before your wedding date.
|  | ☐ | Do a hair and makeup run-through (including wedding veil, if applicable).
| WEEKS TO GO | ☐ | Confirm all transportation plans.
| 2 - 4 | ☐ | Work on seating arrangements for the reception.
|  | ☐ | Finalize arrangements for out of town attendants and guests.
| WEEKS TO GO | ☐ | Confirm details with the photographer, florist, and other vendors.
|  | ☐ | Have final fitting for bridal gown and bridesmaids’ dresses.
|  | ☐ | Write your rehearsal dinner toast.
|  | ☐ | Purchase gifts for the wedding attendants.
|  | ☐ | Compile a list of all of the wedding vendors and wedding party, with contact information. Carry this list with you everywhere you go (just in case).
|  | ☐ | Communicate rehearsal dinner details to those who will attend the rehearsal and rehearsal dinner.
|  | ☐ | Look into where bride, groom and attendants will dress for the ceremony.
| 1 | ☐ | Enclose in envelopes any fees due for easy distribution.
|  | ☐ | Give the caterer a final head count.
| WEEK TO GO | ☐ | Appoint a trustworthy person to bring important items (cake knife, toasting glasses, etc.) to the reception.
|  | ☐ | Appoint someone to act as an “organizer” to handle any last-minute problems.
|  | ☐ | Review final details for those in the wedding party.
|  | ☐ | Get final beauty treatments (manicure, facial, massage, waxing, brow shaping, etc.)
| DAY BEFORE | ☐ | Gather together the following:
| THE WEDDING |  | Something old : symbolizing continuity with family and heritage
Something new : symbolizing optimism and hope for the new life ahead
Something borrowed : an item from a happily married friend or family member
Something blue : symbolizing love and fidelity
|  | ☐ | Confirm honeymoon arrangements.
|  | ☐ | Pack for the honeymoon.
|  | ☐ | Enjoy a relaxing day with family and friends.
|  | ☐ | Attend the rehearsal and rehearsal dinner; give gifts to attendants.
|  | ☐ | Give the rings, and officiant’s fee, to the best man.
|  | ☐ | Try to get some rest.
| WEDDING DAY | ☐ | Post-wedding announcements in the mail.
|  | ☐ | Relax and remain calm.
|  | ☐ | Remember to eat something.
|  | ☐ | Allow at least two hours for getting dressed.
ENJOY THIS ONCE-IN-A-LIFETIME EVENT!